## Sheet 1
Citizens’ Advisory Team Projects
# | Projects | Project Length | Depends on | Lead Agency | Proba- bility | Remarks
Facilities
F-1 | Public Safety Building Phase 2 | 0.0125 | N/A | Friendswood | 90+%
F-2 | Public Works & Parks Building | 0.0125 | N/A | Friendswood | 90+%
F-3 | Activity Building/Civic Center |  | N/A | Friendswood | 90+%
F-4 | Department (VFD) Training Field | 0.0083333 | N/A | Friendswood | 90+%
F-5 | UpgradesFire Station #2 ReconstructionActivities Center | 0.016667 | N/A | Friendswood | 90+%
Facilities Totals
Streets
S-1 | Blackhawk Blvd. Phase 3 | 0.016667 | N/A | Friendswood | 90+%
S-2 | Friendswood Parkway | 0.025 | N/A | Friendswood | 75%
S-3 | Whispering Pines/Friendswood Link Bridge Elevation | 0.0125 | N/A | Friendswood | 75%
Streets Totals
Parks
P-1 | Stevenson Park Walking Trails & Restrooms | 0.0083333 | N/A | Friendswood | 90+%
P-2 | Downtown Pavilion | 0.0083333 | N/A | Friendswood | 90+%
P-3 | Lake Friendswood Additional Parking | 0.00625 | N/A | Friendswood | 90+%
P-4 | City Pool Rehabilitation | 0.0125 | N/A | Friendswood | 90+%
P-5 | Old City Park Additional Parking | 0.00625 | N/A | Friendswood | 90+%
P-6 | Corporal Wesley J. Canning Sportspark (Baker Road Park) | 0.016667 | N/A | Friendswood | 90+%
P-7 | Playground Updates | 0.00625 | N/A | Friendswood | 90+%
P-8 | Sub-regional Park Lundy Lane | 0.016667 | N/A | Friendswood | 90+%
Parks Totals
Drainage
D-1 | De-snagging | 2 | D-9 | Galveston Co. Consolidated Drainage District & Harris County Flood Control District | 100% | In-process.
D-2 | FM2351 Bridge/Road Raising | 10 | D-9 | TxDOT | 60%
D-3 | FM528 Bridge/Road Raising | 10 | D-9 | TxDOT | 60%
D-4 | Terracing - Dixie Farm Rd to FM 2351 | 15 | D-9 & D-8 | Galveston Co. Consolidated Drainage District & Harris County Flood Control District | 60%
D-5 | Terracing - FM 2351 to Whispering Pines | 15 | D-9 & D-8 | Galveston Co. Consolidated Drainage District & Harris County Flood Control District | 60%
D-6 | Terracing - Whispering Pines to FM 528 | 15 | D-9 & D-8 | Galveston Co. Consolidated Drainage District & Harris County Flood Control District | 60%
D-7 | Terracing - FM 528 to W Bay Area Blvd | 15 | D-9 & D-8 | Galveston Co. Consolidated Drainage District & Harris County Flood Control District | 60%
D-8 | Buy Outs | 5 | D-9 | FEMA & Texas Division of Emergency Management | 100%
D-9 | Engineering - Engineering & Environmental Impact Studies | 4 |  | Friendswood | 100%
Drainage Totals
| FOR ALL PROJECTS | TBD